## Estimated time management(plan)
| Task | 2018-10-30 | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-17 | 2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30
1 | Спроектировать базу данных | bar: 2018-10-30 to 2018-10-31
2 | Изобразить схематические рисунки web страниц | bar: 2018-10-30 to 2018-11-01
3 | Построить план выполнения задания | bar: 2018-11-02
4 | Написать часть с моделями | bar: 2018-11-03 to 2018-11-05
5 | Внедрить Spring | bar: 2018-11-06 to 2018-11-11
6 | Написать сервисную часть | bar: 2018-11-10 to 2018-11-15
7 | Разобраться с frontend (Angular или JSF) | bar: 2018-11-16 to 2018-11-21
8 | Создать front | bar: 2018-11-19 to 2018-11-26
9 | Отладка | bar: 2018-11-27 to 2018-11-30

## Estimated time management (real
| Task | 2018-10-30 | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-17 | 2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30
1 | Спроектировать базу данных | bar: 2018-10-30 to 2018-10-31
2 | Изобразить схематические рисунки web страниц | bar: 2018-10-30 to 2018-11-01
3 | Построить план выполнения задания | bar: 2018-11-02
4 | Написать часть с моделями | bar: 2018-11-03 to 2018-11-04
5 | Внедрить Spring | bar: 2018-11-05 to 2018-11-13
6 | Написать сервисную часть | bar: 2018-11-06 to 2018-11-07; 2018-11-10 to 2018-11-15
7 | Разобраться с frontend (Angular или JSF) | bar: 2018-11-16 to 2018-11-21
8 | Создать front | bar: 2018-11-19 to 2018-11-26
9 | Отладка | bar: 2018-11-27 to 2018-11-30

## Work done
| Дата | Проделанная работа
1 | 2018-11-05 | Базовые модели построены и работают с аннотациями Hibernate
2 | 2018-11-06 | Построение каркаса программы
3 | 2018-11-07 | Ознакомление и попытка склейки Hibernate и Spring
4 | 2018-11-07 | Уткнулся в правильное использование аннотаций и файлов конфигураций xml
5 | 2018-11-08 | Усвоил принцип использования @Autowired, @Component, @Service, как писать конфигурационный файл xml и как можно без xml вообще | http://dev-blogs.com/simple-spring-application-using-autowired-annotation/
6 |  | 1. Repacked so that info.mastera is root package
7 |  | 2. Created Config class with Java configuration type at this moment
8 |  | 3.Build base Dao
4. Build One model element with Dao and Service classes to check Spring annotation DI and Hiberate work
5. There is TestExecuter.java for testing in console mode and the moment